## Sheet1
Risk Management
No. | Description Risk | Impaction project | L | S | G | Date of Review | Mitigation Action | Identification Group |  | Cost | 25% | Time Line for Mitigation action(s) | Wes
1 | Iiiness of team member | Probability |  | M |  | 2018-01-01 | Disasters can happen at anytime and anyplace | Provide facilities for meeting | 1 | Estimated Costs | 20% | Week -1
2 | Same Personal work of team members | Consequence |  | M |  | 2018-01-03 | The goal of risk reduction is to reduce the risk to life and property,which includes existing structues. | Attend mettings |  | i. Initial cost | 75% | Week 1 TO Week 5
3 | Hand Work Problem | Perceived likelihood |  |  | H | 2018-01-10 | Mitigation is most effiective when it is based on comprehensive ,long-term plan and Devlopment | To Complete the work |  | ii. Maintenance/operating Costs | 25% | Week 1 TO Week 2
4 | Bugg problem | Consequences |  |  | H | 2018-01-20 | Whenever We faces a Bug mitigation is effective to solve our bug problem | To use the software |  |  |  | Week 5
5 | Internet service problem | Impact | L |  |  | 2018-02-05 | Sometimes internet problem is an issue | Check the internet Connection or make changes in setting to internet | 2 | Benefit to Cost Ration | 40% | #VALUE!
6 | Communication problem | Critical | L |  |  | 2018-02-10 | Some people may face a problem in accesing a software. they may understand or may not. so to reduce this risk mitigation is usefull | Make decisions on plan process and content
7 | Adaptive problem of on project(Uses) | Overall accuracy |  |  | H | 2018-02-20 |  | Review Drafts | 3 | Financing Avaliability | 10% | Week3
8 | Late Delivery | Critical | L |  |  | 2/28/2018 | The cost associated with a late delivery is | Provide Service for fast delivery
9 | Technology Does Not Meet Specifications | Consequences |  | M |  | 3/6/2018 | In order to prevent this from happing,meeting help the customer on a rountine business | Provide proper Specificaion | 4 | Affordability | 10% | Week 2
[9 empty] | 5 | Repetitive Damahes Corrected | 20% | Week 5